## Slide 1
MICROSOFT + GITHUB · INTERNAL
Trainer Checklist
Copilot Hackathon for Non-Developers. Everything that has to be true before nine o'clock — and everything that has to happen after five.
FOUR WEEKS OUT
Scope and commit
THREE WEEKS OUT
Build the environment
ONE WEEK OUT
Chase and confirm
SCOPE AND COMMIT
T MINUS 4 WEEKS · MICROSOFT LEAD + SPONSOR
Prep call held — 90 minutes with the sponsor and IT. Access, publishing, ideas.
Sponsor named — In the room for the last hour. They own the 16:00 triage call.
IT contact named — Approves the laptop software; owns the route off Pages later.
Attendee list agreed — 8 to 24 people, 3 to 6 teams, each with a process expert.
GitHub facilitator booked — Co-delivery is the promise. Confirm the name, not the slot.
Data rules written down — Sample data only. Nothing confidential, nothing personal.
BUILD THE ENVIRONMENT
T MINUS 3 WEEKS · MICROSOFT + GITHUB
Hackathon org created — Temporary org named for the customer and the date. Two owners.
Decommission date fixed — Diarise it now. It goes straight into the closeout email.
Copilot seats assigned — One each, two spares, and one for every facilitator.
Copilot app policy checked — On by default for Business and Enterprise. Confirm it is on.
Pages proven end to end — Publish a throwaway site from Actions before the day, not on it.
Repository template ready — Starter files, the publish workflow, a README a novice can read.
Ruleset applied — So one bad push cannot take a team's site down at half past three.
Actions minutes checked — Public repos are free; private ones draw on the monthly quota.
Prerequisite email sent — Account, username, VS Code and Git, then the app. Git first.
CHASE AND CONFIRM
T MINUS 1 WEEK · MICROSOFT LEAD
Every invitation accepted — Chase by name. Unaccepted invites are the number one delay.
Laptops verified with IT — VS Code, Git and the app installed. github.com reachable.
Room confirmed in writing — Screen, HDMI and USB-C, power at every seat, tables that move.
Access and wifi tested — Visitor passes for both facilitators. A printed card per table.
Ideas triaged — One per team, cut to something publishable by 16:00.
Latest deck downloaded — Today's version of the deck and the one-pager. Not last quarter's.
Catering confirmed — Lunch at the desks keeps the afternoon on time.
Copilot Hackathon for Non-Developers · Internal trainer checklist · Co-delivered by Microsoft and GitHub
1

## Slide 2
Trainer Checklist
THE DAY BEFORE · ON THE MORNING · DURING THE DAY · AFTER
THE DAY BEFORE
BOTH FACILITATORS
Full dry run — Clone, change it in the app, push, watch Actions, open the site.
Room set up — Team pods, screen visible from every seat, power at the front.
Projector and cables tested — In the actual room, with the actual laptop, with the adapters.
Printouts ready — Agenda, ground rules, wifi card, prompt crib sheet, triage form.
Backup plan agreed — A spare laptop, a mobile hotspot, two spare accounts.
ON THE MORNING
FROM 08:00
In the room an hour early — Screen on, deck open, the demo site already live in a tab.
Everything re-tested — The room was locked overnight. Assume something has changed.
Door and laptops covered — One facilitator signing people in, one fixing setups.
First fifteen minutes held — Reserved for stragglers. Start the content at 09:15, not setup.
DURING THE DAY
STAGE BY STAGE
09:00 Frame it — Read the data rules out loud. One sentence per team on what ships.
10:00 Build it — Circulate constantly. Nobody stuck for more than five minutes.
13:00 Make it real — Push early. A live site at lunchtime beats a perfect one at five.
14:30 Publish it — Every site live and reachable. Screenshot each one for the record.
16:00 Decide — The sponsor triages in the room: keep, park, or hand to IT.
Photos and quotes captured — With consent. You will want them for the follow-on case.
AFTER THE DAY
WITHIN ONE WEEK
Repositories exported — The same week. Do not wait for the closeout email to do this.
Closeout email sent — Microsoft-branded, with the decommission date filled in.
Outputs handed over — Triage list, guardrail set and playbook to sponsor and IT.
Feedback requested — Within 24 hours, while the day is still fresh in the room.
Environment decommissioned — On the stated date. Confirm it in writing to the sponsor.
Follow-on booked — The route to production for whatever the sponsor kept.
IN THE BAG
Two HDMI cables · USB-C and Mini DisplayPort adapters · a clicker · a four-way extension lead · a mobile hotspot · a spare laptop already signed in to a spare GitHub account · printed wifi cards · the triage form · sticky notes and markers · the latest deck on a USB stick as well as in the cloud.
Internal document. The hackathon organisation is temporary and is deleted on the agreed date — say so in the room, in the prerequisite email and in the closeout email. GitHub Pages is static hosting; outside GitHub Enterprise Cloud, published sites are public. Anything a team wants to keep must leave the organisation before it closes.
Copilot Hackathon for Non-Developers · Internal trainer checklist · Co-delivered by Microsoft and GitHub
2